## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-001 | As a developer, I need to find and prepare the ANPR dataset so that I can train the ANPR model. | Must have | None | Anil S | Completed
Sprint 1 | Sprint 1 | US-002 | As a developer, I need to train the YOLOv8s model with ANPR data so that the system can accurately detect number plates. | Must have | US-001 | Anil S | Completed
Sprint 1 | Sprint 1 | US-003 | As a developer, I need to research and select a proper OCR model for reading plate data so that the detected plates can be converted to text. | Must have | US-002 (Detection) | Anil S | Completed
Sprint 1 | Sprint 1 | US-004 | As a developer, I need to set up the basic Streamlit application framework so that I have a platform for integration. | Should have | None | Anil S | Completed
Sprint 2 | Sprint 2 | US-005 | As a developer, I need to find and prepared my own video dataset the ATCC dataset so that I can train the ATCC model. | Must have | None | Anil S | Completed
Sprint 2 | Sprint 2 | US-006 | As a developer, I need to train the YOLOv8s model with ATCC data so that the system can accurately classify vehicle types. | Must have | US-005 | Anil S | Completed
Sprint 2 | Sprint 2 | US-007 | As a developer, I need to integrate the ANPR model and OCR logic into the Streamlit app for still images. | Must have | US-003, US-004 | Anil S | Completed
Sprint 2 | Sprint 2 | US-008 | As a developer, I need to add basic logging and error handling to the application so that issues can be tracked easily. | Should have | US-004 | Anil S | Completed
Sprint 3 | Sprint 3 | US-009 | As a developer, I need to integrate the ATCC model into the Streamlit app for still images. | Must have | US-006, US-007 | Anil S | Completed
Sprint 3 | Sprint 3 | US-010 | As a developer, I need to implement video inference logic for both ANPR and ATCC so that the app can process video files. | Must have | US-007, US-009 | Anil S | Completed
Sprint 3 | Sprint 3 | US-011 | As a user, I want the UI/UX to be enhanced and intuitive so that the application is easy to use. | Must have | US-010 | Anil S | Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Spring Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13
[8 empty] | 38 | 4 | 4 | 4.5 | 4.5 | 4 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 1
SPRINT 1 BACKLOG
US-001 | TASK-001 | Find and acquire diverse ANPR training and validation datasets. | 2025-11-15 | 2025-11-16 | Anil S | Data Gathering | Completeed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TASK-002 | Set up YOLOv8 environment and initialize ANPR model training. | 2025-11-17 | 2025-11-18 | Anil S | Model Training | Completeed | 4 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | TASK-003 | Research and select final OCR model/library for plate reading. | 2025-11-19 | 2025-11-19 | Anil S | Research | Completeed | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | TASK-004 | Setup basic Streamlit application framework (main page, structure). | 2025-11-20 | 2025-11-22 | Anil S | Web Development | Completeed | 5 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-005 | TASK-005 | Find and prepare ATCC vehicle classification datasets. | 2025-11-23 | 2025-11-24 | Anil S | Data Gathering | Completeed | 5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 2 | 1 | 0 | 0
US-006 | TASK-006 | Train and validate the YOLOv8s model with ATCC data. | 2025-11-25 | 2025-11-26 | Anil S | Model Training | Completeed | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 2 | 0
US-007 | TASK-007 | Integrate ANPR/OCR logic into the Streamlit app for still images. | 2025-11-27 | 2025-11-28 | Anil S | Integration | Completeed | 5 | 0 | 0 | 2.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | TASK-008 | Add basic error handling and logging to the application. | 2025-11-29 | 2025-11-30 | Anil S | Testing | Completeed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
SPRINT 3 BACKLOG
US-009 | TASK-009 | Integrate the ATCC classification model for still images. | 2025-12-01 | 2025-12-01 | Anil S | Integration | Completeed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | TASK-010 | Implement and optimize video inference logic for both ANPR/ATCC. | 2025-12-02 | 2025-12-04 | Anil S | Video Processing | Completeed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | TASK-011 | Enhance UI/UX and visual output of the Streamlit application. | 2025-12-05 | 2025-12-07 | Anil S | UI/UX | Completeed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | TASK-012 | Perform final end-to-end testing and write documentation. | 2025-12-08 | 2025-12-10 | Anil S | Validation | Completeed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day 3 | Initial ANPR dataset found had poor label quality/format mismatch. | Held a dedicated data cleaning session and standardized label conversion script.
S1 | Day 7 | YOLOv8s training failing due to GPU memory constraints on the current machine. | Optimized batch size and transferred the training job to a machine with higher VRAM capacity.
S2 | Day 11 | Difficulty finding a suitable, open-source OCR model with sufficient accuracy for diverse number plate fonts. | Researched and selected an off-the-shelf OCR library (like EasyOCR) for rapid integration and testing.
S2 | Day 15 | The ATCC dataset required significant cleaning and re-labeling to match the desired vehicle classification categories. | Allocated 4 additional hours to manually verify and correct labels for the ATCC dataset subset being used.
S3 | Day 17 | Initial integration of the two models (ANPR and ATCC) into the Streamlit app caused namespace conflicts. | Refactored the inference code to ensure clear separation of model loading and function calls.
S3 | Day 21 | Video inference performance was unacceptably slow due to frame-by-frame processing overhead. | Implemented optimized video processing using a multi-threading approach for I/O operations.
S3 | Day 25 | Getting unexpected caching issues with Streamlit causing model re-loading on every user interaction. | Used Streamlit's @st.cache_resource decorator to manage and stabilize model loading.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2025-11-15 | 2025-11-22 | Anil S | Integrating initial model tests immediately after training | Focusing solely on dataset perfection before model training | Daily communication on ANPR data quality and progress | Successfully completed ANPR training and OCR selection (US-001, US-002, US-003)
2 | S2 | 2025-11-23 | 2025-11-30 | Anil S | Writing basic documentation for new feature integration (e.g., ATCC) | Delaying integration testing until the end of the sprint | Maintaining the basic Streamlit app framework setup (US-004) | Successfully integrated ANPR/OCR into the app and completed ATCC training (US-007, US-006)
3 | S3 | 2025-12-01 | 2025-12-10 | Anil S | Running performance checks on video processing logic | Over-optimizing minor UI elements before core video functionality works | Prioritizing Must-Have features (video inference US-010, US-011) | Improved video inference performance and completed core application logic